| Table of Contents | Page |
| --- | --- |
| 1. Comprehensive Multi-agency Coordination and Planning – Non CEO MIG Grant 2. Local Multi-Agency Service Delivery Pilot Projects 3. Joint Efforts with Vocational Rehabilitation and Centers for Independent Living 4. Joint Efforts with Work Force Development Employment and One-Stop Services 5. Peer Support and Mentoring Initiatives to Encourage and Support Employment 6. Staff Training for Case Management Which Reflects Self-Determination Principles, Person- Centered Planning and Consumer-Directed Models 7. Specific Mental Health Services and Employment Focus of MIG Project 8. Specific emphasis of MIG Project on Employment of Persons with Developmental Disabilities 9 Youth Transition Programs 10 Joint Efforts with Asset Development Projects as Related to Work Incentives 11. Enhanced Use of Medicaid Home & Community-Based Waivers in Supporting Employment 12. Coordination with SSA Ticket Program 13. Housing Related to Employment Activities 14 Transportation Related to Employment Activities 15. Assistive Technology and Durable Medical Equipment as related to Employment 16 Self-employment and Entrepreneurial Activities | 2 3 4 5 7 9 10 12 14 17 18 20 20 21 22 23 |

| 1. Comprehensive Multi-agency Coordination and Planning – Non CEO MIG Grant |  |
| --- | --- |
| State | Recent Activities |
| Maryland South Dakota | ### 3rd Quarter 2005 – The Maryland MIG project is part of a joint effort with a US Department of Labor funded project called Maryland WorkFORCE Promise and is partnering with the Maryland Department of Disabilities (MDOD) and the Division of Rehabilitation Services (DORS) on an Employment Systems Transformation Steering Committee. The goal of the committee is to establish common employment definitions, values driven outcomes, to create a vision/map for what the system should look like, and to define initial action steps toward the vision. Maryland Department of Disabilities recently submitted a state plan to the Governor and the legislature as to how the Department of Disabilities will move forward in achieving their mission to work with all state agencies to empower individuals with disabilities to achieve their personal and professional goals. Information on the Employment Systems Transformation Steering Committee and the Plan submitted to the Governor can be found at http://www.mdworkforcepromise.org/statewide%20activities.htm 2nd Q 2005 - Goal of new interagency “Career Development Team Model” is that at least 12 South Dakotans with disabilities will receive assistance in obtaining employment and other support services, including PAS through the career development team model. The career development team model to include Dept. of Labor, VR staff, BPAO staff, an employed person with a disability, a human resource person and a job coach/developer that will meet with consumers who wish to utilize this effort to assist them in successfully obtaining employment. The MIG staff is in the process of informing potential consumers about the team model concept in order to recruit them into the process. 4th Q 2005 – Work that was initiated on the concept of a Career Development Teams is to be implemented in 2006. 2nd Q 2006 - The Sioux Falls Career Development Team met & finalized an application process as well as timelines for submission of contact information, when appointments would be sent out, deadlines on returning applications and selection of applicants. The team will begin working with individuals in late August or early September |
| States with Activities pre 2005: New Hampshire Alaalll |  |

| 2. Local Multi-Agency Service Delivery Pilot Projects |  |
| --- | --- |
| State | Recent Activities |
| Florida Pennsylvania Virginia Wisconsin Wyoming | Florida 1st Q 2006 – There are four Pilot sites for the Florida MIG project and there is one Florida Agency for Persons with Disabilities staff in each of the four sites. They are to support the Agency’s 5-year employment initiative The four pilot sites are: Jacksonville (Area 4); Orlando (Area 7); Palm Beach County (Area 9); and Tampa (SunCoast Area. Forty percent of the employment liaisons’ time will be spent expanding the employment of people with disabilities by organizing training and TA, 40% will be spent on implementation of the Florida Freedom Initiative, and 20% will be spent on the Business Leadership Networks. 2nd Q 2006- All of the employment liaisons have been employed with various types of training completed. They are making progress in promoting the employment of people with disabilities, marketing supported employment and assisting with the BLNs and FFI. 2nd Q 2006 - All of the employment liaisons have been employed with various types of training completed. They are making progress in promoting the employment of people with disabilities, marketing supported employment and assisting with the BLNs and FFI. State MIG project established pilot demonstration project. One in a rural area and one in an urban area. They are to work with One Stop employment centers (called Career Links in Pennsylvania). 1st Q 2005 - Urban and Rural Projects ended March 31, 2005. Currently evaluating the value of the demonstration approaches. Local demonstration projects of models of coordination and referral between youth in transition school programs and BPAOs, One- Stops, Employment Networks, and the VA Office for Protection and Advocacy. Three local projects were funded under a contract with Virginia Commonwealth University. Collaborating with Capital Area Workforce Investment Board in employment orientation activities for students. 4th Q 2005 – MIG working with Workforce Investment Board enhanced Chesterfield Schools internship service by adding supervised Career Assessment & connecting with One-Stop. 12 students enrolled & 9 successfully completed. All 9 completed Virginia employment agency applications , registered for service, & enrolled in CATC Youth Services Program at Workforce Center. 1st Q 2005 - Family Care Medicaid waiver pilots in 5 counties involving self-directed services and person-centered planning for work supports. Information on Family Care pilots at http://dhfs.wisconsin.gov/LTCare/ Wyoming – 1st Q 2005 – Goal is to create a single integrated community case plan approach for delivery of all public and private services in the community. 4th Q 2005 - Pilot Projects involving review of service gaps and overlaps in closed cases for four groups of consumers in three geographically different communities. |

| 3. Joint efforts with Vocational Rehabilitation and/or Centers for Independent Living. |  |
| --- | --- |
| State | Recent Activities |
| Utah Nevada New Hampshire New Mexico Oregon Wisconsin Washington South Carolina Maine | Utah 1st Q 2005 - Creating a new position in the State Office of Rehabilitation (USOR) to develop a system that coordinates job seekers on the "supply-side" with the "demand-side" of employment opportunities. Goal is to develop an effective system among agencies serving a person with disabilities that coordinates job seekers with employment opportunities in the Utah workforce. 3rd Quarter 2005 – Utah State Office of Rehabilitation (USOR) hired a “supply-side” position and has proceeded to hold focus groups to define the role of this position. Results from this study will be integrated into the logic model for this initiative. 4th Q 2005 – MIG staff provided training to rural Vocational Rehabilitation staff and reconfirmed MIG staff's desire and availability to make presentations to groups of individuals receiving Vocational Rehabilitation services. 3rd Quarter 2005 - Established active database provided by New Hampshire Voc Rehab; converted data of job seeker occupational goals; analysis of job goals among VR underway. Data obtained on patterns of self-employment. Identification of partnerships underway with community based programs and job training programs. Contracted with Institute on Disability at Univ. of NH to provide education & training. and technical assistance on supportive competitive employment, customized employment strategies, workplace-based supports and assistive technology to providers and agencies to improve employment outcomes. 1st Q 2006 - Project goal is to maximize employment for individuals in Medicaid Buy-In & other Medicaid populations by NH Voc Rehab cross-data match & identify under-employed and/or expand employment services to help individuals reach highest level of economic independence. Completing work plan between Voc Rehab and the School of Community Economic Development at Southern NH Univ. (SNHU) who will team up to provide a VR customer data base and analyze occupational demands and labor trends, conduct outreach with selected job sectors and collaborate on workforce development models. A comparison has been completed on occupation projections against jobs obtained & original employment plan. Consultations conducted with two business sectors on workforce development. MOU established between SNHU & CLFund for IDAs to VR self-employed clients. 3rd Quarter 2005 – In a joint effort between the MIG project and the Department of Vocational Rehabilitation, the Department of Vocational Rehabilitation Outreach Coordinator employed/trained Medicaid Buy-In Peer Associates. Program now has program knowledgeable personnel in a much larger area of the state. 4th Q 2005 – Plan to have 6 Peer Associates in 2006 4th Q 2005 -MIG Project contracted with five Centers for Independent Living to organize the community forums the project is holding in their communities in order to get input for project's strategic plan. Contracted with two Centers for Independent Living to replicate their transportation model in three new counties. Washington 1st Q 2006 - Contracted with State Rehabilitation Council to conduct conference on employment that includes advance work with consumers to prepare portfolios, with employers on concepts of customized employment, and personal interviews. MIG Project staff contributed to development of online resource for consumers and employers MIG Project staff began collaboration with the Yakama Nation to develop an American Indians with disabilities conference that focuses on employment issues. 1st Q 2006 - Contracted with the Washington Initiative for Supported Employment to provide training and technical assistance to individuals, families, educators, and providers. South Carolina 4th Q 2005 – MIG project partners with and supports the local Aging and Disability Resource Center. Maine 2nd Q 2006 - MIG staff completed first comprehensive. needs assessment for state VR agency. Results of this assessment are guiding internal agency system improvement efforts as well as targeting continued MIG supports. Looking to help agency develop better data support as well as explore an outcome-based payment system Maine 2nd Q 2006 - Increasing the number of people who receive job supports through the Division for Rehabilitative Services after entering the Mental Hygiene Administration's supported employment sites. The strategy is to change the Mental health data system ( MAPS-MD program) to allow caseworkers in the Division of Rehabilitative Services to access this database. |
| States with Activities pre 2005: Connecticut, Missouri, Nebraska, New Mexico, Oklahoma, Rhode Island See |  |

| 4. Joint Efforts with Work Force Development Employment and One-Stop Services |  |
| --- | --- |
| State | Recent Activities |
| Alaska California Kansas Minnesota Louisiana Massachusetts Nevada Utah Virginia Wisconsin Washington West Virginia Hawaii Nebraska Rhode Island | 2005 - A project assistant with the Alaska Workforce Investment Board is assigned one-quarter time to assist the Alaska Works Initiative. He is responsible for outreaching to employers and coordinating the Business Leadership Network. 1st Q 2006 - Project coordinated job center efforts to include people with disabilities in all job fairs. 2nd Q 2005 - Worked with Employment Development Department to issue information to Workforce Development system to educate One-Stops and Workforce Investment Boards about CHIIP (MIG project) and encourage brochure dissemination. to their consumers. 1st Q 2005 - One Benefit Specialist is placed at a Kansas Workforce Development Center (WDC) one afternoon per week to act as a "Disability Navigator", assisting consumers with disabilities, and providing technical assistance for WDC staff. 4th Q 2005 – MIG Project offers disability training at Workforce Development Centers located throughout Kansas. Several of the trainings will be conducted in 2006. 1st Q 2006 - Two Workforce trainings were offered during the first quarter. Participants evaluated the sessions very positively. A Benefits Specialist continues to be placed part-time at a KWDC in one county. Three other Specialists made a total of seven KWDC outreach contacts during the first quarter. 2nd Q 2006 - Joint effort with the Governor’s Workforce Development Council related to preparation of a report on “Integrating Individuals with Disabilities into the Workforce.” May 2006 Report available at http://www.gwdc.org/publications.htm#2006 MIG provided disability awareness training for 300 Work Force Center staff. 1st Q 2006 - Contracting with New Horizons Independent Living Center to facilitate work incentive workshops for persons with disabilities & the One Stop system; recruit & train additional workshop coordinators; & facilitate interaction between consumers, the One Stops and disability support programs. 1st Q 2006 – MIG staff is developing a plan with the Workforce Development System to increase access to employment services; disseminating promising practices through MassWorks newsletter. MassWORKS issue on working with business is being finalized. Issue on evidence based practice is in development. Meeting was held with key workforce development system staff and plans will be finalized in May. 2nd Q 2006 - Plans are underway to build capacity of the business service units within the One-Stops to better address disability related issues. Training and TA is underway, addressing both provider capacity issues and systems issues. 3rd Quarter 2005 - MIG and Medicaid Buy-In staff conducted a workshop at the Department of Employment, Training and Rehabilitation's Fall in-service training conference. 3rd Quarter 2005 - The Utah’s Business Employers Team committee ( a part of MIG project) is reviewing electronic tools that could be used to match employer’s needs with job seekers with disabilities. Utah's Dept of Workforce Service also has invested heavily in improving job matching tools. These are increasingly being used by Utah employers. 2nd Q 2005 – Worked with Capital Area Workforce Investment Board to develop an employment orientation program for job-seeking youth with disabilities. 4th Q 2005 – MIG working with Workforce Investment Board enhanced school internship service by adding supervised Career Assessment & connecting with One-Stop. MIG provided Assistive Technology Tool kits to 6 One-Stops. 2nd Q 2006 – Goal is to increase use of Virginia's One-Stop workforce system by current recipients of SSA disability benefits and other Virginians with disabilities interested in employment. Using Disability Program Navigator positions (DPNs), established through WIG, as liaison to facilitate access between BPAOs and One-Stop customers and staff through the multi-partner video conferencing initiative. Disability Program Navigators (DPNs) helped facilitate transition from Workforce Incentive Grant Round IV, ending June 30th, to the Cooperative Agreement in conjunction w/Virginia Employment Commission. DPNs helped set up video conferencing trainings in regions they serve to promote use of MIG-funded video conferencing equipment. 1st Q 2005 - Three 'business liaisons' at One Stops are piloting new methods of engaging employers in hiring persons with disabilities, developing trainings and materials and are training providers in business liaison. 2nd Q 2005 - Collaborative work with One Stop system, Department of Vocational Rehabilitation, and 12 school districts on School to Work project; 50 students with DD will exit school into job placements. 4th Q 2005 – MIG project staff conducted work incentives training for staff at four Work Source sites 3rd Quarter 2005 – MIG staff provided information and training on Personal Care Employment Services (State’s PAS program) to One-Stop Centers, Vocational Rehabilitation District office staff and the general public. Q 2005 - Collaborating with Workforce Development Council in needs assessment effort and mapping employment opportunities 1st Q 2005 – Partnering with the Department of Labor and Workforce Development systems to increase use and accessibility of employment services for people with disabilities. Providing statewide training to One stops and Workforce Development making their services accessible to people with disabilities. 2nd Q 2005 - Job Fair planning in collaboration with the RI One-Stops. |
| States with Activities pre 2005: Iowa, Maine, New Hampshire, Oregon, Pennsylvania, South Dakota Alaalll |  |

| 5. Peer Support and Mentoring Initiatives to Encourage and Support Employment |  |
| --- | --- |
| State | Recent Activities |
| Massachusetts Minnesota Kansas Oregon Vermont Nebraska New Mexico Illinois Wisconsin Kansas Washington Virginia | 4th Q 2005 & Plans for 2006 - Peer-to-peer benefits support pilot has been expanded to include an additional community. Participants have been recruited and screened. Training curriculum has been developed and evaluation methods designed. 1st Q 2006 – State is implementing and evaluating a pilot peer-to-peer (consumer-to-consumer) mentorship program to disseminate information about work opportunities and work incentive programs. 18 individuals participated in benefits and employment training to become peer leaders. Each participant developed an outreach plan that is currently being implemented. Follow-up sessions are scheduled with the peer leaders and evaluation data is being collected. 2nd Q 2006 - Peer leaders report contact with 213 individuals about benefits and employment. 100% of survey respondents reported that the contact was helpful and that they learned something new. Over ½ of individuals contacted by Peer leaders reported being less concerned about losing their benefits if they work than they were before their contact. 1st Q 2006 - Signed contract to develop curriculum to train peer-to-peer supporters around employment. Sent 200 surveys to potential peer support providers to assess interest in participation 1st Q 2006 - Survey of former Kansas Youth Employment Academy participants regarding employment and access to health care. Early results include: 13.3% had no doctor visits in the past year, 13.3% say that expense is a barrier; 20% are afraid of losing insurance by working too much. All ten Centers for Independent Living in state offering mentoring services to promote employment of persons with disabilities under a contract with MIG. Over 100 peer mentors providing mentoring services 1st Q 2005 - New peer projects negotiated with three separate consumer advocacy groups, representing consumers with physical, developmental, and psychiatric disabilities. MIG is supporting the conversion of existing peer support groups and peer curricula to a greater emphasis on community inclusion through employment. Also developing and publicizing a referral network for trained peer leaders willing to participate in policy planning and evaluation meetings for state and local agencies. 3rd Quarter 2005 - One Developmental Services pilot and two Mental Health pilots under way; all initiating outreach to employers, retraining of agency staff for employment support functions, and brief mentorship placements for people with disabilities 1st Q 2006 -Support mental health recovery & self-management education; support implementation of VT CHOICES curriculum for employment planning and management. (To be done in conjunction with peer projects.) Consumer Network (People with disabilities organized by local Independent Living Center and League of Human Dignity) provides information to consumers, One-Stops and employers after they are trained on presentation skills. Intent is to change culture toward employment. 3rd Quarter 2005 – At end of quarter Department of Vocational Rehabilitation Outreach Coordinator employed/trained seven Medicaid Buy-In Peer Associates. Program now has program knowledgeable personnel in a much larger area of the state. 4th Q 2005 – Plan to have 6 Peer Associates in 2006 2nd Q 2006 - 4 part-time Peer Associate's and 2 full-time BPAOs provided Working Disabled Individuals (WDI) info to 273 individuals. This represents a 69% increase from previous quarter due to increased activities of the PA's. Peer Associates (PA) provide information on the WDI program, application assistance, problem solving & other support services to those interested in the WDI program. They are Individuals w/disabilities, not necessarily enrolled in NM WDI program. 3rd Quarter 2005 – Developing peer mentoring program to current Buy-In enrollees who are potential volunteer mentors and to those in the HCBW program in attempt to "match" the HBWD enrollees with volunteer mentors. Also developing and implementing a training curriculum for both components, to track the communication between the mentors and their peers, and to track eventual outcomes of the peer mentoring project 4th Q 2005 - Have completed the training manual development, mentor training implementation and "matching" components of the program. Currently the mentors are working with their "mentorees" to help them understand how to approach finding the right job, and what they need to do to become employed. Plans for 2006 - Planning to develop an Advisory Committee from the Network of Centers for Independent Living to serve in an advisory role for the peer mentoring project 2nd Q 2006 - Tracking the communication between the mentors and the mentorees and tracking the "job" outcomes of the peer mentoring project 4th Q 2005 – Implemented pilot project on curriculum for vocational planning with peer support for persons with mental illnesses. 2nd Q 2005 - MIG funds were used to sponsor the Kansas Youth Leadership Forum, attended by 35 youth and 42 youth mentors. 2nd Q 2006 - Consistent with overall enrollment in the Medicaid Buy-In, enrollment in Buy-In of youth age 20 to 30 dropped by 14% from December 2005 (79 to 68) to June 2006. 1st Q 2005 - Facilitating employment of at least 40 people with mental health impairments as peer counselors by implementing an enhanced Peer Support Program (PSP) that adds an employment specialization component to general PSP certification curriculum. Basic PSP is being implemented. Certification training and testing materials are finalized; 25 applicants completed first training segment. 2nd Q 2005 - 75 consumers have completed the required 40 hours of training. Additional training planned to increase pool of those having received basic training, in order to meet targeted number of direct employment outcomes. 2nd Q 2006 - Basic Peer Support Program has continued. Sufficient number of consumers has completed basic training from which up to 40 can be chosen to complete enhanced curriculum. Goal is to generate up to 40 direct employment outcomes, e.g. graduates will begin work for agencies providing mental health 1st Q 2006 – Have developed and am implementing a work incentives training and peer support program for individuals with serious mental illnesses who are interested in working. Pilot project includes peer education on incentives, workshops for peer trainers on balancing work and mental illness, workplace interpersonal skills and attitudes, and job seeking. Contract developed w/Laurie Mitchell Employment Center in Arlington, Virginia. It has assembled a project advisory board & hired project coordinator. |

| 6. Staff training for case management which reflects self-determination principles, person- centered planning and consumer-directed models |  |
| --- | --- |
| State | Recent Activities |
| Indiana Minnesota Kansas Wisconsin New Hampshire Massachusetts | Indiana 1st Q 2006 – Partnering with Medicaid Chronic Disease Management program to train Nurse care managers in work incentives. Embed an emphasis on employment as a priority in the Medicaid system in Indiana. MIG staff provided training to 55 county workers and other stakeholders to promote paradigm shift related to enhancing the employability of people with disabilities. MIG project contracted for the training of state staff, Centers for Independent Living, community DD organizations and home health agencies on promotion of independence, self sufficiency, and self direction. State is implementing waiver for a reform of their long-term care system which includes vocational goals. Waiver project is called Family Care. Information on Family Care pilots at http://dhfs.wisconsin.gov/LTCare/ All Family Care pilots are now implementing Person Centered planning for vocational goals and educating local Family Care governing councils on needs for employment supports. Strategy is to increase employment of people with disabilities, and gather outcome data, by building employment information into Wisconsin’s Long Term Care system’s functional screens, and by automating part of Developmental Disability (DD) process Mental health screen developed with employment information incorporated. Analysis of Physical Disability and DD LTC screen produced ways of determining employment and PAS status. Further development of modeling of part of DD process. Wisconsin 1st Q 2005 - Pilots in 5 counties involving self-directed services and person-centered planning for work supports continue to develop their work. Statewide planning group for promoting self-directed services formed. 3rd Quarter 2005 - Service provider training and technical assistance on person centered planning (PCP) and self directed supports 4th Q 2005 – “Lessons Learned” paper on Self Directed Services has been prepared. 1st Q 2006- MIG Project conducted 10 trainings/TA visits with Community Organizations re: person-centered-planning (PCP) and self directed supports. Provided training and outreach in northern more rural part of state targeted at case managers, hospital discharge planners, and social service providers to ensure they have knowledge on options for personal care and health care needs to facilitate employment. Also provided technical assistance on customized employment approach and person-centered planning for individuals with disabilities. Independent living service coordinators trained to include Ready-to-Work skills in their programs. MIG Project supports Training Calendar which coordinates provision of information for professionals on best practices for achieving employment for people with disabilities. Assessment of state agency training needs has been completed and inventory of training resources has been conducted. Training needs assessment has been finalized. Training calendar is now available online at www.massworks.org/tcal 4th Q 2005 - Mass Works Newsletter is distributed by mail and electronically to over 2400 disability and employment providers in Massachusetts . Access recent newsletters at http://www.massworks.org/index.php |
| See |  |

| 7. Specific mental health services and employment focus of MIG project |  |
| --- | --- |
| State | Recent Activities |
| Alaska Utah Vermont Wisconsin Maryland Massachusetts Minnesota Washington Virginia Maine | MIG funds were used to fund a vocational specialist in the state mental health agency to build employment infrastructure and has focused on needs and resources assessment. Employment specialist developed a Behavioral Health employment manual. Department of Behavioral 4th Q 2005 - 96 people were served through the evidence-based supported employment grant; 30 work full time and 49 work part-time; a survey of mental health block grantees indicated that an additional 206 persons are receiving supported employment services. 1st Q 2006 - 70 people were served through the evidence-based supported employment grant; 59 (84%) are working – 34 full time and 26 part-time. An evidence-based manual for staff and consumers has been developed. Several programs are adding supported employment to their menu of services. 2nd Q 2006 - Approximately 130 consumers, 100 family members and several hundred providers benefited from a variety of training and outreach activities specific to the employment of people with mental illness and/or traumatic brain injury. Conducted and evaluated demonstration project on use of PAS to support working people with mental illness. MIG staff has developed role of service broker to facilitate entry into EPAS program. Provider manual has been developed and have developed training for consumers and personal assistants. Program has decreased use of mental health services and enabled maintaining employment. 1st Q 2005 - New peer projects negotiated with three separate consumer advocacy groups, representing consumers with physical, developmental, and psychiatric disabilities. Supporting the conversion of existing peer support groups and peer curricula to a greater emphasis on community inclusion through employment. Also developing and publicizing a referral network for trained peer leaders willing to participate in policy planning and evaluation meetings for state and local agencies. 1st Q 2006 - 1st Q 2006 –Supporting mental health recovery & self-management education; support implementation of VT CHOICES curriculum for employment planning and management. 2nd Q 2006 –Strategy is to support mental health recovery & self-management education; support implementation of VT CHOICES curriculum for employment planning and management. (To be done in conjunction with peer projects.) Project proposals obtained from community agencies; grant negotiation in progress. 4th Q 2004 - A workgroup of consumers and service providers met regularly and developed a curriculum for vocational exploration groups for people with mental illness. Information on employment supports, incentives, and self-advocacy was disseminated at a consumer conference and in a newsletter. Wisconsin 2nd Q 2005 – First draft of career development curriculum and trainings for people with mental illness has been completed. 4th Q 2005 – Implemented pilot project on curriculum for vocational planning with peer support for persons with mental illnesses. 2nd Q 2006 - Two new MH vocational peer groups identified and networking plans initiated. MIG project is coordinating with the state mental health agency to evaluate the current delivery of supported employment services in Maryland and identifying options for improvement. The joint effort will evaluate other states' practices in the areas of: evidence-based supported employment interventions; benefits counseling; rate structure and provider reimbursement; coordination across state agencies. 2nd Q 2005 - Report completed by The University of Massachusetts’s - Institute for Community Inclusion 1st Q 2006 - Through a contractor, a program evaluation/cost study will be developed to help the State follow the flow of money through the mental health system related to supported employment services. 1st Q 2006 - State is streamlining and reducing paperwork for the eligibility process for individuals with a disability who enter into the Mental Hygiene Administration and are referred to the Division of Rehabilitative Services for employment supports. Make systems changes to the mental health data program that allows caseworkers in the Division of Rehabilitative Services to access this database. State has developed policy and provides that acceptance into the mental health system provides for presumptive eligibility for state vocational rehabilitation. 2nd Q 2006 – Goal is to increase the number of people from 1500 individuals who are receiving supported employment supports. Through a contractor, a program evaluation/cost study will help the State follow the flow of money through the mental health system by 12/31/06 Increase the number of people who receive job supports through the Division for Rehabilitative Services after entering the Mental Hygiene Administration's supported employment sites. The strategy is to change the Mental health data system ( MAPS-MD program) to allow caseworkers in the Division of Rehabilitative Services to access this database. Study underway to assess the effect of treatment for depression on work. 1st Q 2006 – Evaluating the Supported Education and Employment (SEE) program of the Department of Mental Health, with the goal of increasing the number who are competitively employed 50. Assessing fidelity to evidence-based practice models; developing and implementing a targeted intervention for under-performing programs to improve employment outcomes. 2nd Q 2006 - Negotiated with Department of Mental Health and MassHealth privacy offices to determine procedures for linking administrative databases. Obtained IRB approval for site visits (Phase 1) and analysis of existing administrative data (Phase 2). Gathered input from DMH stakeholders regarding sampling strategy for site visits. Completed analysis of effect of adequate treatment for depression on work. 4th Q 2005 – Developed interagency agreement to train MN Tribal communities in maximizing Medical Assistance supports pertaining to mental health and employment. Washington 2nd Q 2005 - Facilitating employment of people with mental health impairments as peer counselors by implementing an enhanced Peer Support Program (PSP) that adds an employment specialization component to general PSP certification curriculum. 75 consumers have completed the required 40 hours of training. Additional training planned to increase pool of those having received basic training, in order to meet targeted number of direct employment outcomes. 1st Q 2006 – Have developed and implementing a work incentives training and peer support program for individuals with serious mental illnesses who are interested in working. Pilot project include peer education on incentives, workshops for peer trainers on balancing work and mental illness, workplace interpersonal skills and attitudes, and job seeking. Contract developed w/Laurie Mitchell Employment Center in Arlington, Virginia. It has assembled a project advisory board & hired project coordinator. 2nd Q 2006 - Laurie Mitchell Employment Center (LMEC) project team reviewed training materials from various sources and developed a draft agenda for an eight-day training. Curriculum is currently being refined and will be piloted with two groups of 12 people in August and October. 2nd Q 2006 - Maine's mental health services agency is under court consent decree to increase services, including employment services. External consultant report recommends department hire 2 benefits specialists. MIG helping agency plan this effort and coordinate with overall system |
| States with Activities pre 2005: New York See |  |

| 8. Specific emphasis of MIG Project on Employment of Persons with Developmental Disabilities. |  |
| --- | --- |
| State | Recent Activities |
| Alaska Kansas Vermont Washington Oregon Massachusetts | Alaska 1st Q 2006 - The Division of Senior & Disabilities Services (DSDS) set a performance target to increase the number of DD waiver recipients receiving supported employment services. Baseline data from the most recent state fiscal year ending June 30, 2005 is 320 individuals. 1st Q 2006 - Project staff worked with the Developmental Disability Waitlist Committee; as a result, priority consideration for services will be given to transition-age youth 2nd Q 2006 - Project staff worked with the legislature and the Division of Senior & Disabilities Services to secure a $3 million increment to remove people from the developmental disabilities waitlist; priority will be given to youth transitioning from school to work. Kansas– 2nd Q 2004 – MIG project has contracted for the training of state staff, Centers for Independent Living, community DD organizations and home health agencies on promotion of independence, self sufficiency, and self direction. Vermont 1st Q 2005 - New peer projects negotiated with three separate consumer advocacy groups, representing consumers with physical, developmental, and psychiatric disabilities. Supporting the conversion of existing peer support groups and peer curricula to a greater emphasis on community inclusion through employment. Also developing and publicizing a referral network for trained peer leaders willing to participate in policy planning and evaluation meetings for state and local agencies. 2nd Q 2006 - Project proposals obtained from community agencies; grant negotiation in progress. Washington 2nd Q 2005 - Collaborative work with Department of Vocational Rehabilitation, One Stop system and 12 school districts on School to Work project; 50 students with DD will exit school into job placements. 4th Q 2005 - Pilot project for interagency youth placement effort in Seattle area 1st Q 2006 – MIG Project helped plan conference on new Developmentally Disabled Working Age Adult Policy which has been adopted which prioritizes use of service dollars to support employment. Statewide forum was attended by 130 representatives from provider organizations, county programs and department staff that focused on implementation of the DD Working Age Adult policy. This policy raises the bar on the use of service dollars for individuals with DD by requiring all participants to work or prepare for employment. 2nd Q 2006 - Conducted training in several counties on implementation of the State Developmentally Disabled Working Age Adult policy and addition of Medicaid buy-in to eligibility groups for DD HCBS waiver services. Oregon 1st Q 2006- MIG Project convened one-day roundtable forum on supported employment for persons with developmental disabilities. The focus was on identifying effective strategies and activities utilized in other states. Contracted with Oregon Council on Developmental Disabilities to operate a transition training project. 2nd Q 2006 - Convened Developmental Disabilities Supported Employment work group. Agreed to subsidize state DD agency participation in NASDDDS-sponsored, multi-state network to renew DDSE effort Massachusetts 1st Q 2006 - Goals is for 24 clients of the Department of Mental Retardation (DMR) with service plans achieve employment through improved service delivery and systems change coordinated through regional employment services teams. The strategy is to: establish a state-wide and regional Employment Solutions Teams for DMR clients; improve employment practices through TA and training with providers; develop program monitoring systems and modify administrative and funding practices for improved outcomes. Regional teams are meeting and have begun to identify the 24 clients for intervention. Statewide team has formed and will begin meeting in April. The statewide team will be responsible for development of an employment strategic plan for DMR. Training needs are being identified. 2nd Q 2006 - Statewide and regional teams (4) are all active. A wide range of policy and practice issues have been identified; development of a strategic plan is underway. Direct service training needs have been identified and training has been planned. Technical assistance activities are ongoing. |
| See |  |

| 9. Youth transition programs |  |
| --- | --- |
| State | Recent Activities |
| Maryland Massachusetts Maine Oregon Utah Wisconsin Alaska California Connecticut Iowa Kansas Minnesota Missouri Nebraska Rhode Island South Dakota Utah Vermont Virginia Washington District of Columbia New Jersey Wisconsin New Hampshire North Carolina South Carolina | 1st Q 2006 - MIG has issued an RFP for a consultant to provide a comprehensive overview of the state agency supports for youth as they transition into workforce. 1st Q 2006 - Identified target populations of transition-age disabled youth (15-22) & care coordinators who work with them to coordinate health care and employment outcomes. Met with DPH advisory board and staff to discuss joint care coordinator training. Began care coordinator curriculum development. MIG staff authored Disability Issues article on Transition to Employment for Youth. Article at http://www.masschec.org/Youth/transitionarticle.cfm 2nd Q 2006 - Attended Department of Public Health Transition Advisory Board meeting; identified training needs of care coordinators; drafted curriculum; began revision of SS Benefits Guide; published article on Transition Planning 1st Q 2006 - Goal in Maine MIG CEO Strategic Plan included that the state will better support young people with disabilities who are transitioning from school to work in order to increase job readiness and work skills, as well as the number and quality of early work experiences for youth with disabilities Extensive distribution of the final strategic plan with focus on youth in transition one of the six strategic priorities. Meetings have been held with planning groups in other education, transition and youth support systems to discuss strategic plan, possible common strategic priorities and action steps. 2nd Q 2006 – MIG Project invited to be a member of Governor's new initiative to engage youth in school and help connect to employment and continued education. 2. Project focus and budget agreed upon for partnership training with statewide transition network The partnership program with the state transition network will focus on disclosure issues for youth with disabilities who are entering the labor market as they exit high school - best strategies for disclosing in resume, interview, after hire. 1st Q 2006 - Contracted with the Oregon Parent Training and Information Center to convene a statewide conference on transition for teachers, vocational professionals, consumers and advocates. 2nd Q 2006 - Transition conference held April 12-13. 440 attended 30 sessions (largest ever attendance). Training developed and first held May 18, 25, June 1. 27 student and family members attended; 8 completed multi-evening series. 1st Q 2006 - Training provided to 22 teachers/staff of the Utah Schools for the Deaf and Blind; The Training and Education Committee of the Governor's Committee on Employment of People with Disabilities created a plan to present findings to school district special ed directors, Disability Resource Centers, etc. 1st Q 2006 - Goal in MIG –CEO Strategic Plan is to increase the number of students with disabilities who have information about employment options and supports through Pathways programs. Strategy is to research and design effective means of providing students with disabilities the information and supports needed to make decisions about their futures after high school and to prepare for the transition to employment or post-secondary education. Topic areas include employment and educational options, the Individual Education Program (IEP) process and rights, person-centered planning, self determination, self advocacy and benefits counseling. Current status - Contract initiated, planning and training meetingss held, curriculum finalized, providers contracted, began designing research. MIG project staff works closely with Division of Business Partnership/Alaska Workforce Investment Board to implement its 5 year Youth Transition & Mentoring Grant. A Transition summit was held. MIG Project staff works with the youth grantees in the Youth Transition Project. 12 of the 50 enrollees were employed in 4th Quarter of 2005. Alaska 1st Q 2006 - The 4 youth intermediary grantees funded by the Youth In Transition (YIT)served 135 youth this quarter; 26 are employed. Staff worked with the Alaska Workforce Investment Board’s Youth Council on strategies for ensuring all youth, including youth with disabilities, are prepared for Alaska’s jobs. YIT funding from the Office of Disability Employment Policy ends September 30, two years early. Project staff facilitated several meetings to identify sustainability strategies upon termination of grant funding. 1st Q 2006 - Project staff worked with the Developmental Disability Waitlist Committee; as a result, priority consideration for services will be given to transition-age youth 2mf Q 2006 - The 4 youth intermediary grantees served 150 youth this quarter; 60 are employed. A variety of resources (i.e. in-kind support, legislative increment, local government, related grants) have been secured to continue intermediary services in all 4 locations. Problems/Issues YIT funding from the Office of Disability Employment Policy ends September 30, two years early. Project staff facilitated several meetings to identify sustainability strategies upon termination of grant funding. 3rd Quarter 2005 - Provided materials, staff support, & presented at annual California Youth Leadership Forum. Began outreach campaign targeting Postsecondary Education audiences. Initiated young adult pilot program, quarterly case conferencing, developed youth-specific power point and shared regionally and nationally. Outreach has doubled the number of young adults receiving benefits counseling. 3rd Quarter 2005 - A youth with disabilities employment transition workshops have been held with approximately 200 case managers; Kansas 2nd Q 2005 - MIG funds were used to sponsor the Kansas Youth Leadership Forum, attended by 35 youth and 42 youth mentors. 4th Q 2005 - Benefits Specialists conducted 14 presentations targeting transitioning youth. 82 individuals ranging in age from 16 to 29 are now enrolled in Medicaid Buy-In program. There was a slight increase in percentage of enrollees in this age group during the fourth quarter 2nd Q 2005 - Coordination with a major youth transition grant effort (Dept of Labor youth transition grant). Also, initial development of local educational transition efforts. 1st Q 2006 - Provided materials on Medicaid Buy-In & linkage line for 230 parents & youth at Transition Summit 2nd Q 2006 - Supported the Minnesota Department of Education (MDE) and Project C3 (Connecting Youth to Communities and Careers) to strengthen transition services by: creating mentoring and early work opportunities, supporting the development and promotion of best practices and innovative strategies, and by coordinating planning and information distribution. Finalized plans for Minnesota Department of Education and MIG project joint effort in coordinated resource mapping. Careers & resource presentation to 30 transition students & parents, Planning internship programs 4th Q 2005 – Establishing and continuing on-campus workshops for transition, conducting needs assessments of campuses and develop and implement the planned initiatives. Pilot project developed and implementation underway. Needs assessment conducted. Workshop held (November 2005) for college career counselors. 3rd Quarter 2005 - Trained educators & HHS Eligibility staff about work incentives resulted in youth becoming employed & seeking higher education, receiving benefits analyses & an increase in Medicaid Eligibility staff referrals. 1st Q 2006 -. 8 pilot youth have received BPAO & IEPs added employment goals. The MIG’s Youth in Transition Workgroup prepared report on “Health Care Gaps in Rhode Island for Children with Disabilities: Challenges and Proposed Strategies” Intent was to identify the health benefits available for children with disabilities, those available for adults with disabilities, the "gaps" between the two, and to develop strategies to bridge these gaps. A health care gaps' chart has been completed based on a draft of the report) 2nd Q 2006 - Contracted with a consultant to provide at least 6 days of statewide training on work incentives to consumers, family members, representative payees, service provider staff and other advocates; staff will continue to publish the "Tips Newsletter" at least 3 times a year. Training sessions were held in April & June. 254 participated in these events. A specific focus of sessions was transition-age youth & their families. Newsletter was sent to over 1350 individuals. Curricula for teachers and transition coordinators and families and youth have been developed. 1st Q 2006 - Training provided to 22 teachers/staff of the Utah Schools for the Deaf and Blind; The Training and Education Committee of the Governor's Committee on Employment of People with Disabilities created a plan to present findings to school district special ed directors, Disability Resource Centers, etc. 1st Q 2005 - Youth transition peer meetings sponsored. 2nd Q 2006 – MIG helped sponsor Independent Living Youth Summit. 2nd Q 2005 - Work incentives brochure for Department of Education & transition-age population, developed. Brochure has been reproduced and distributed, including to Centers for Independent Living and BPAOs. Working with Capital Area Workforce Investment Board to develop an employment orientation program for job-seeking youth with disabilities; planned for the fall 2005. 2nd Q 2006 - Continuing employment orientation activities for transition-age students in conjunction with One-Stop/Capital Area WIB.Ongoing requests (e.g., by school staff, BPAOs, CILs) for copies of MIG-funded benefits planning brochure “Benefits Planning for a Brighter Future” will initiate a 3rd printing. 2005 - Collaborative work with Department of Vocational Rehabilitation, One Stop system and 12 school districts on School to Work project; 50 students with DD will exit school into job placements. Pilot project for interagency youth placement effort in Seattle area 3rd Quarter 2005 - Produced draft Youth transition guide. 2nd Q 2005 – MIG project staff at the Division of Disability Services in partnership with the NJ Department of Education, Office on Special Education Programs co-sponsored Dare to Dream Student Leadership Conferences which were held at six area colleges, one high school and County Special Service Office. Reached over 1,700 transitioning students in New Jersey. 4th Q 2005 - The Division of Disability Services (MIG project) in partnership with The Boggs Center on Developmental Disabilities gathered project partners, developed a curriculum and teacher's guide that was mailed to all New Jersey School districts and presentations were made to transition coordinators and regional stakeholders. The curriculum has been sent out to New Jersey School districts. 1st Q 2006 - Four Dare to Dream in 2006 Student Leadership Conferences for High School Students are scheduled for May and June of 2006. Drafted SSI waiver application for transition age students. Presented at statewide Youth Transition Leadership Forum. Compiled issue briefs. Local workgroup collaborations were developed to further waiver development. Began implementation of plan to introduce benefits counseling in one locality. Wisconsin 2nd Q 2005 – MIG is planning to help develop work experience opportunities for blind students in secondary education 2nd Q 2006 - 15 students received counseling, conference call held for provider sites, research design approved, Peer Power pilot completed, mentors trained at 2 sites, data collected and review, evaluation process initiated. Forums held to develop a Youth Transition Tool Kit report 4th Q 2005 - Plans are near completion for a statewide transition -age youth conference. 2nd Q 2005 - Training of special education transition coordinators on Section 1619 work incentives held. |
| States with Activities pre 2005: See |  |

| 10. Joint Efforts with Asset Development Projects as related to work incentives |  |
| --- | --- |
| State | Recent Activities |
| Wisconsin New Hampshire Washington Ohio Washigton | MIG project staff working with national experts and project staff on asset development initiative for persons with disabilities MIG project staff working with Southern New Hampshire University School of Community Economic Development which is one of the partners in the National Asset Accumulation and Tax Policy Project directed University of Iowa’s Law, Health Policy, and Disability Center 1st Q 2006 – Goal is to support the creation of an environment in which individuals may self-direct their life experiences in the pursuit of their career goals, including their awareness and use of Individual Development Accounts (IDAs) to build assets and increase self-sufficiency. MIG Project staff conducted five outreach presentations to encourage awareness and use of IDAs. Developed and distributed flyer to promote use of IDAs for self-employment. Provided technical assistance to Spokane DVR staff and Neighborhood Action program to increase use of IDAs. 1st Q 2006- Developing an RFP with the MIG- Olmstead Advisory Committee to contract for a Asset Development Feasibility Study. A contractor will examine challenges and opportunities to the design, development, and implementation of an Ohio asset building strategy for persons with disabilities who are or may become Medicaid beneficiaries. 1st Q 2006 – Goal is to support the creation of an environment in which individuals may self-direct their life experiences in the pursuit of their career goals, including their awareness and use of Individual Development Accounts (IDAs) to build assets and increase self-sufficiency. MIG Project staff conducted five outreach presentations to encourage awareness and use of IDAs. Developed and distributed flyer to promote use of IDAs for self-employment. Provided technical assistance to Spokane DVR staff and Neighborhood Action program to increase the use of IDAs. 2nd Q 2006 - Incorporated information about IDAs available in the state into work incentives training curriculum; disseminated this information to benefits planners, those funded by BPAO and others. |

| 11. Enhanced use of Medicaid Home & Community-Based Waivers in Supporting Employment |  |
| --- | --- |
| State | Recent Activities |
| Alaska Indiana New Hampshire Connecticut Iowa Illinois North Dakota South Carolina Washington Iowa Minnesota Wyoming | 1st Q 2006 - The Division of Senior & Disabilities Services (DSDS) set a performance target to increase the number of DD waiver recipients receiving supported employment services. Baseline data from the most recent state fiscal year ending June 30, 2005 is 320 individuals. 1st Q 2006 - Project staff worked with the Developmental Disability Waitlist Committee; as a result, priority consideration for services will be given to transition-age youth 1st Q 2006 – Partnering with Medicaid Chronic Disease Management program to train Nurse care managers in work incentives. Embed an emphasis on employment as a priority in the Medicaid system in Indiana. 1st Q 2006 – Goal is to increase access to personal care services (PCS) statewide under the HCBC-ECI (Elderly and Chronically Ill) waiver services to provide people with disabilities the services needed to go to work. Strategies include: Implement certification process for OQAs (Other Qualified Agencies) to provide PCS. 2. Provide training and education to service planners about PCS options. 3. Conduct quality and assurance of billing thru new 2006 long-term care data system and conduct a file review of PCS difficulties reported Request for Proposals made public in March. Process has begun to hire and approve four part-time nurses to do personal care services monitoring and quality assurance. 2nd Q 2005 - Legislation advancing for tie in of Medicaid to ABI and DMR waivers approved by legislature. Work on amending waivers initiated; Amendments include continuing PCA assistance for persons currently on the PCA and ABI waivers and participating in the Medicaid Buy-In program and who age into the home care program for elders program; cost analysis initiated; Focus groups with consumers and case managers were held to determine why employment supports were not used and changes were made. Home and Community Based Services specialists met with 2 providers to provide employment TA and resulted in 9 consumers obtaining employment based on TA. A report was completed based on the Focus groups. 3rd Quarter 2005 – Developing peer mentoring program to current Buy-In enrollees who are potential volunteer mentors and to those in the HCBW program in attempt to "match" the HBWD enrollees with volunteer mentors. Also developing and implementing a training curriculum for both components, to track the communication between the mentors and their peers, and to track eventual outcomes of the peer mentoring project 4th Q 2005 - Have completed the training manual development, mentor training implementation and "matching" components of the program. Currently the mentors are working with their "mentorees" to help them understand how to approach finding the right job, and what they need to do to become employed. Plans for 2006 - Planning to develop an Advisory Committee from the Network of Centers for Independent Living to serve in an advisory role for the peer mentoring project 3rd Quarter 2005 - MIG has a work group on Personal Assistance Services and Home and Community Based Services (PAS/HCBS Initiative) which is intended to identify potential areas of collaboration among initiatives and systems; and to improve access to PAS/HCBS services to employed citizens of North Dakotan's with disabilities. 3rd Quarter 2005 – State is requesting an amendment to the MR/RD waiver to add adult attendant care for those that can self-direct their own care. 4th Q 2005 - Provided information to include in the Medicaid waiver packets about 1619(b) and the state's buy-in program. 3rd Quarter 2005 - Promoting amendment to DD Home and Community Based Care waiver for including Buy-In as an eligibility group. 2nd Q 2006 - Conducted training in several counties on implementation of the State Developmentally Disabled Working Age Adult policy and addition of Medicaid buy-in to eligibility groups for DD HCBS waiver services. 4th Q 2005 - Work continued to add self-direction option to the HCBS waivers which will expand employment supports. A presentation was made to legislators on the self-direction option. This activity will continue into 2006. 2nd Q 2006 – – “Review of Minnesota’s Vocational and Employment Services for Individuals with Disabilities: Focus on Day Training and Habilitation” Prepared for the Minnesota Department of Human Services Disability Services Division by the Lewin Group. February 2006 Report available at http://www.dhs.state.mn.us/main/groups/disabilities/documents/pub/dhs_id_057670.pdf Goal of assessment was to identify the type, number, and distribution of Supported Employment supports funded through HCBS waivers. The analysis also includes review of the county implemented system to identify the quality of MN's employment support infrastructure. 2nd Q 2006 – MIG is involved in discussions to change Medicaid Waivers to allow Waiver participants to continue receiving services even if they participate in the Buy-In program. |
| States with Activities pre 2005: Idaho, South Dakota, Pennsylvania, Wisconsin and Missouri Alaalll |  |

| 12. Coordination with SSA Ticket Program |  |
| --- | --- |
| State | Recent Activities |
| Indiana Nebraska Kansas | Indiana 1st Q 2006 – MIG is sponsoring Employment Network Forum to provide information on new Ticket regulations to increase participation in program. Employment Network Forum scheduled for July 2006. 4th Q 2004 – Nebraska MIG developed a Ticket to Work Web site developed at http://www.nebraskatickettowork.com/default.htm Kansas 1st Q 2005 - Mailings were sent to 66,500 SSA beneficiaries in Kansas who received "tickets". Benefits Specialists received approximately 488 calls requesting information; 14 people enrolled in Medicaid Buy-In program (Working Healthy); and approximately 100 individuals were referred to Employment Networks Ns and Vocational Rehabilitation for employment assistance. |
| States with Past Activities pre 2005: Maine, New Hampshire, Vermont, Washington, Nevada and Utah See |  |

| 13. Housing Related to Employment Activities |  |
| --- | --- |
| State | Recent Activities |
| North Dakota Rhode Island | North Dakota MIG Housing Task Force interacts with MIG staff on the barriers to housing as it relates to employment opportunities for North Dakota citizens with disabilities. To identify barriers, priority issues, clarify questions, research services and to develop resources to housing as it relates to employment. This effort will continue into 2006. 2nd Q 2006 - Housing Task Force is moving forward with legislation regarding “Visitability” law in North Dakota. Sub-committees of the task force are actively working towards established goals. Housing Work Group formed by MIG project. Goal is to improve capacity and access to affordable / accessible housing that is coordinated with long-term care support, and provide support in navigation of the housing system. Conducted 2 focus groups to assess consumers’ perceptions of barriers & unmet needs across the housing-needs continuum. 1st Q 2006 - The Housing Workgroup met once; informational support was provided for implementation of a RI home modifications revolving fund that would provide loans for accessibility modifications of homes of people with disabilities and the elderly. |
| States with Activities pre 2005: Alaska and Louisiana |  |

| 14. Transportation Related to Employment Activities |  |
| --- | --- |
| State | Recent Activities |
| Florida Oregon Rhode Island New Jersey Oklahoma Rhode Island Wisconsin South Carolina | Florida 1st Q 2006 – MIG will be conducting 5 Transportation Forums across the state. Target audience will be self-advocates and their family members. Participants will be invited to voice their concerns and ideas to improve Florida's transportation services for workers with disabilities. Contractor will provide a full report based on consumer input and recommendations. One forum completed; four scheduled. 2nd Q 2006 - Five transportation forums are completed and minutes of each forum have been submitted to APD; 75% of the participants were people with disabilities and their families. Draft report has been provided to APD. Oregon 1st Q 2006 - Participated in the Oregon United we Ride Planning Workgroup. Met with representatives from the Oregon Department of Transportation to continue planning transportation activities and to begin to select targeted counties for transportation projects. 2nd Q 2006 - Continued to meet with ODOT staff and its United We Ride group. Latter agreed to serve as Project workgroup. Researched options/processes for assisting communities in developing transportation plans and services. Attended regional transportation planning conference to identify possible strategic models. 1st Q 2006 - "Best Practices and Innovative Programs Transportation Report" is due for completion this summer. 1st Q 2 3rd Q 2005 - New Jersey has a Five Year Transportation Plan for Working People with Disabilities developed with support by the MIG project in partnership with the Alan M. Voorhees Transportation Policy Institute at Rutgers. 4th Q 2005 - A transportation summit was held in December with one day targeted on consumers and the second day on legislators. Resource Material : Final Transportation Study Report “Meeting the Employment Transportation Needs of People with Disabilities in New Jersey – 2005 “ available at http://policy.rutgers.edu/vtc/documents/TransEq.DDS_ExSum.pdf 1st Q 211st Q 2006 - Building on the extensive database of transportation service information collected as part of the NJ Division of Disability Services 5 year Transportation Plan study, the Alan M. Voorhees Transportation Center at Rutgers, The State University of New Jersey in partnership with the NJ Division of Disability Services will create a one-stop internet "web portal" to improve access to information on transportation options for people with disabilities. 2nd Q 22ndd Q 2006 - Accomplishments: Transportation services inventory, focus groups, design and testing of web portal for internet mapping. 1st Q 2005 - Oklahoma Alliance for Public Transportation began in January 2005 and includes members from Ok Dept of Trans; Tulsa Transit Auth; Central Oklahoma Public Transit Auth; Ok Dept of Health; Dept of Rehab Services ; and OHCA(Medicaid agency) . Monthly meetings address challenges and offer solutions to transportation challenges. 4th Q 2005 - "United We Ride" partnered with Oklahoma Alliance for Public Transportation to present a workshop addressing the variables and barriers in the creation of a reliable and affordable transportation system for persons with disabilities. Rhode Island MIG project has Transportation Work Group and research on best practices and innovative transportation programs for people with disabilities has been accomplished for MIG Transportation Workgroup. 1st Q 2006 - "Best Practices and Innovative Programs Transportation Report" is due for completion this summer. 2nd Q 2006 - RTI successfully applied during the quarter to participate in the August CTAA Institute for Transportation Coordination. This is an intensive planning and training forum and will be the basis for this outcome's activities through the end of the year and into 2007. Rural employment transportation project now underway and preparing to hold Transportation Summit in 2006. MIG contracted with Centers for Independent Living to replicate their transportation model in three new counties. 1st Q 2006 - First Northwest Wisconsin Transportation summit held 3rd Quarter 2005 - MIG had University of South Carolina conduct study of transportation as a major barrier to employment in South Carolina.. |
| Other States with Past Activities | Alaska, Maine, South Dakota and South Carolina |

| 15. Assistive Technology and Durable Medical Equipment as related to Employment |  |
| --- | --- |
| State | Recent Activities |
| Arkansas Louisiana Virginia Wisconsin | 1st Q 2006 - Disability conference scheduled for July 5-7, sponsored by Arkansas VR assistive technology program, the MIG project, and other disability agencies. 1st Q 2006 - Have developed a contract with LATAN to implement manage and promote The Assistive Technology Marketplace: Louisiana’s Assistive Technology Classifieds, a recycling database that provides persons with disabilities access to a centralized, internet & telephone-based clearing house of previously owned assistive technology devices. 4th Q 2005 - Interagency team (VR and AT programs) developed portable Assistive Technology tool kits & displays for employer events & trainings to draw businesses w/education/resources/demonstrable devices. Brochures w/displays: Workforce Network, Transition Benefits, Emergency Evacuation Procedures. Working with Workforce Investment Board, MIG provided AT kits to 6 One-Stops 2nd Q 2006 – Department of Rehabilitative Services continues to promote use of the AT kits in One-Stop centers; recently added large print keyboards & posters describing AT kit features to all sites. MIG-funded Business Expo Display was used in 3 sites this quarter: 2nd Q 2005Developed action plan for the improvement of AT maintenance and repair. Developed curriculum and planned training and resource lists on AT products, acquisition and usage. 4th Q 2005- Completed paper on Electronic Durable Medical Equipment 1st Q 2006 - Agenda and tentative dates set for trainings, three papers sent to RESNA for possible publication.. 2nd Q 2006 - Facilitator for Universal Design symposium contracted, planning meetings held, 3rd annual Maintenance and Repair Symposium held, plans discussed for internet based system, AT trainings, publicity, and agenda planned for Speech Therapists. |
| States with Activities pre 2005: Connecticut, Idaho, Iowa, New Hampshire, Vermont and Missouri |  |

| 16. Self employment and Entrepreneurialship |  |
| --- | --- |
| State | Recent Activities |
| Alaska Hawaii North Dakota Iowa Minnesota South Dakota Vermont Wisconsin | 4th Q 2005 Micro-enterprise Resource Guide developed and available from MIG web site at http://www.alaskaworksinitiative.org/merg/ 2nd Q 2006 - Created self-employment partnership with AMHD- Steadfast-VSA 2nd Q 2005 - Statewide Self Employment Network developed with regional groups forming a local network on self employment. 3rd Quarter 2005 - Four of the eight regions in North Dakota have started their own self-employment network to cover their regions. Partnering with ND VR to complete focus groups in North Dakota and on reservations. 4th Q 2005 – North Dakota Chapter of Association of Programs for Supported Employment (APSE) has taken ownership and will continue to promote self employment. Resource Material: Material developed under North Dakota MIG project related to Self Employment can be found on North Dakota MIG Web site at http://165.234.216.166/medicaid/employ/index.php Iowa 4th Q 2005 and Plans for 2006 - Self-employment workshops were held for Medicaid Buy-In enrollees and for service providers, consumers, families, Area Education Agency staff, voc rehab staff, transition specialists, case managers and county funders. These activities to continue in 2006. 2nd Q 2006 - Self-Employment seminars planned for 9/06. 4th Q 2005 - Four business development contracts were initiated to provide technical assistance for Minnesotans with disabilities (micro-enterprise activities). Began planning for national Business Leadership Network (BLN) conference in October which Minnesota is hosting. South Dakota 1st Q 2006 - Consultant is scheduled to provide self-employment and small business development training to interested consumers and benefits specialists in South Dakota.. 1st Q 2006 - Sponsored self-employment expert-panel discussion for rehab professionals with Governor's Committee on Employment of People with Disabilities Wisconsin 1st Q 2005 - Integration of tax and work incentives project agreed to focus on promotion of self-employment incentives. Wisconsin 2nd Q 2005 – Materials developed for consumers interested in business incubation. |
| States with Activities pre 2005 : Alaska, New Hampshire, Vermont and Idaho |  |