| 1. Personal Assistance Services (PAS) Program Planning & Fiscal Estimating |  |
| --- | --- |
| State | Recent Activities |
| Florida Kansas North Dakota Oklahoma Arkansas Hawaii Indiana Michigan North Carolina Wyoming Missouri | Florida 1st Q 2006 – State MIG will contract to conduct a study to increase understanding of the strengths and weaknesses of current coverage of Personal Assistance Services (PAS) under Florida’s HCBS waivers. Study will explore expansion options, impact on Medicaid expenditures, and produce a report with findings and recommendations. 2nd Q 2006 Due date of interim report #1 is September 10, 2006; interim report # 2 October 15, 2006; and Final Report December 1, 2006. 3rd Q 2006 Interim report #1 on PAS will be submitted to Agency for Persons with Disabilties at the end of November 2006. The report will provide a national view of PAS and how Florida currently implements this program through its waivers 1st Q 2006 - Kansas has made the decision to pursue an alternative option to the Independence Plus Waiver in order to provide personal assistance services to individuals with developmental and physical disabilities. State plans to submit a State Plan Amendment, Optional Choice of Self-Directed Personal Assistance Services (Cash and Counseling), available under the Deficit Reduction Act, to provide personal assistance and related services to individuals with physical and developmental disabilities who wish to enroll in Working Healthy. 1st Q 2005 – MIG is developing an initiative to improve PAS services and attempt to become fully eligible under MIG requirements. 1st Q 2005 - PAS has been a part of Oklahoma's approved Medicaid State Plan. Oklahoma's Premium Assistance Program went into effect on 1-1-05, providing coverage for previously ineligible working disabled persons who earned over the limit. Personal care assistants are available in the home, and to assist in situations involving transportation for health care purposes. 2nd Q 2005 Self-Directed Care Act - SB 1015 passed When implemented to allow for community based services over Long Term Care facilities; to provide choice and control of service providers; to allow for money to follow the person; and to establish a fiscal intermediary system within the 1915© waiver 1st Q 2005 – MIG Formed a PAS committee and will be studying other states' workplace PAS services and utilization, developing a proposal, and submitting the proposal to the Medicaid agency. 2nd Q 2005 - MIG PAS committee has reviewed current services and barriers to PAS in workplace, in preparation for preparing recommendations. Q 2005 – Developing plans to gather input from stakeholders on improving PAS program through focus groups to be held in August – October 2005. 1st Q 2006 – After evaluation of situation it was determined that Hawaii had sufficient availability of PAS services statewide under Medicaid waivers. 2nd Q 2006 –Satisfied the Lewin formula and CMS criteria related to PAS. MIG staff contributed to policy change whereas supported employment as a PA service added to the DD/MR waiver. .. Indiana 1st Q 2005 – State entered into contract with Indiana University to conduct a needs assessment and feasibility study for expanding PAS capacity. Indiana 2nd Q 2005 - PAS needs assessment and feasibility study with recommendations was completed and is being distributed. 1st Q 2005 - MIG project is beginning discussions with other state agencies related to changes in Personal Care benefits. Strategy involves: 1) Develop beneficiary data collection system, 2) Research other state's models & results, 3) Gather data on participant's experiences, 4) Analyze program options & limits and 5) Recommend implementation. 3rd Quarter 2005 – State will initiate the State process needed to change the personal care services language to allow these services to be used in the workplace. 4th Q 2005 - 12/15/06-Medicaid office provided draft language to amend State Plan Amendment for review by partners. Mid-January meeting set for further discussion. 2nd Q 2006 - CMS approved draft language submitted by MSA in May. MSA is addressing related questions to state plan & expects to submit actual amendment in July with an expected completion of 9/30/06. MSA attestation letter submitted with 07 MIG application echoes same. 1st Q 2005 - PAS Workgroup met four times to discuss definitions & decide on approach for enhancing services. Members decided that Medicaid State Plan amendment was a preferable avenue for enhancing services compared to waiver options. Agreement upon what constitutes PAS continues to evade the group. 3rd Quarter 2005 The Advisory Council has now reached a consensus of what constitutes PAS. Survey used to conduct consumer survey of needs should be completed by the end of October 2005. 4th Q 2005 - Data is currently being compiled from the survey created to identify consumer needs. A strategy for service delivery was developed. The workgroup is now focused on implementation. Wyoming 2nd Q 2005 - Developmental Disabilities Department has agreed to craft a follow-on PAS measurement process. 4th Q 2005 - Research conducted on PCA infrastructure; needs assessment underway; preliminary plans developed. Needs assessment conducted of advocacy and self-advocacy groups in four Missouri regions. Plans developed to replicate PCA pilot project in four additional communities. |